## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2201-swen-261-d-TheBestSWENTeam
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | User Story | Acceptance Criterion | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | E. V. S., 9/30/20. | As a player I want to resign from the game so that I can exit the game. | Given that I or my opponent resign when playing a game then I expect the game to end. |  | B.B, 10/18/20 |  | As a Player I want to play against a NPC Player so that I can play a game without another person. | **Given** that there is no human opponent available **when** I log in and am in the lobby **then** I expect to be able to play against a NPC. | Not yet tested
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | E. V. S., 9/30/20 | As a user I want to capture my opponent's pieces so that I can win the game. | Given that my opponent has caught some of my pieces when playing a game then I expect to see the number of pieces they have captured. |  | B.B, 10/18/20 |  | As a player I want to spectate a game so that I can watch another game and get better at checkers. | **Given** that I am logged in **when** I navigate to the lobby **then** I expect to be able to spectate a game. | Not yet tested
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | H. L. M., 10/1/10 |  | Given that I have caught some of my opponent's pieces when playing a game then I expect to see the number of pieces I have captured. |  | B.B, 10/18/20
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | H. L. M., 10/1/10 | As a user I want to take a turn so that I can advance the game. | Given that I see a game board when I am on the game page then I expect to be able to move my pieces. |  | B.B, 10/18/20
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | H. L. M., 10/1/10 |  | Given that it is not my turn when I am playing a game then I expect my opponent to take their turn. |  | B.B, 10/18/20
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | H. L. M., 10/1/10 |  | Given that the game is over when both me and my opponent have finished our turns then I expect to see an exit option. |  | B.B, 10/18/20
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | H. L. M., 10/1/10 |  | Given that my move was not valid when it's my turn then I expect to see an error message explaining why my move was not valid. |  | B.B, 10/18/20
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | H. L. M., 10/1/10 |  | Given that I have moved my piece when it's my turn the* I expect to see a submit button to submit my turn. |  | B.B, 10/18/20
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | H. L. M., 10/1/10 |  | Given that it is my turn when I am playing a game then I expect that I cannot exit the game. |  | B.B, 10/18/20
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | H. L. M., 10/1/10 |  | Given that it is not my turn when I am playing a game then I expect that I cannot exit the game |  | B.B, 10/18/20
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | H. L. M., 10/1/10 |  | Given that I have pressed the exit button when the game has finished then I expect to be taken back to the home page. |  | B.B, 10/18/20
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | H. L. M., 10/1/10 | As a user I want to undo my move so that I can redo my move. | Given that I did not like my move when it's my turn but before I submit my turn then I expect to be able to hit the backup button. |  | B.B, 10/18/20
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | H. L. M., 10/1/10
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | H. L. M., 10/1/10
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | H. L. M., 10/1/10